## sheet1
name | status | startDate | dueDate | 8/22 | 8/23 | 8/24 | 8/25 | 8/26 | 8/27 | 8/28 | 8/29 | 8/30 | 8/31 | 9/1 | 9/2 | 9/3 | 9/4 | 9/5 | 9/6 | 9/7 | 9/8 | 9/9 | 9/10 | 9/11 | 9/12 | 9/13 | 9/14 | 9/15 | 9/16 | 9/17 | 9/18 | 9/19 | 9/20 | 9/21 | 9/22 | 9/23 | 9/24 | 9/25 | 9/26 | 9/27 | 9/28 | 9/29 | 9/30 | 10/1 | 10/2 | 10/3 | 10/4 | 10/5 | 10/6 | 10/7 | 10/8 | 10/9 | 10/10 | 10/11 | 10/12 | 10/13 | 10/14 | 10/15 | 10/16 | 10/17 | 10/18 | 10/19 | 10/20 | 10/21 | 10/22 | 10/23 | 10/24 | 10/25 | 10/26 | 10/27 | 10/28 | 10/29 | 10/30 | 10/31 | 11/1 | 11/2 | 11/3 | 11/4 | 11/5 | 11/6 | 11/7 | 11/8 | 11/9 | 11/10 | 11/11 | 11/12 | 11/13 | 11/14 | 11/15 | 11/16 | 11/17 | 11/18 | 11/19 | 11/20 | 11/21 | 11/22 | 11/23 | 11/24 | 11/25 | 11/26 | 11/27 | 11/28 | 11/29 | 11/30 | 12/1 | 12/2 | 12/3 | 12/4 | 12/5 | 12/6 | 12/7 | 12/8 | 12/13 | 12/14 | 12/15 | 12/16 | 12/17 | 12/18 | 12/19 | 12/20 | 12/21 | 12/22 | 12/23 | 12/24 | 12/25 | 12/26 | 12/27 | 12/28 | 12/29 | 12/30 | 12/31 | 1/1 | 1/2 | 1/3 | 1/4 | 1/5 | 1/6 | 1/7 | 1/8 | 1/9 | 1/10 | 1/11 | 1/12 | 1/13 | 1/14 | 1/15 | 1/16 | 1/17 | 1/18 | 1/19 | 1/20 | 1/21 | 1/22 | 1/23 | 1/24 | 1/25 | 1/26 | 1/27 | 1/28 | 1/29 | 1/30 | 1/31 | 2/1 | 2/2 | 2/3 | 2/4 | 2/5 | 2/6 | 2/7 | 2/8 | 2/9 | 2/10 | 2/11 | 2/12 | 2/13 | 2/14 | 2/15 | 2/16 | 2/17 | 2/18 | 2/19 | 2/20 | 2/21 | 2/22 | 2/23 | 2/24 | 2/25 | 2/26 | 2/27 | 2/28 | 3/1 | 3/2 | 3/3 | 3/4 | 3/5 | 3/6 | 3/7
Complete project Execution | Done | 8/22 | 2024-08-12
Requirement | Done | 8/23 | 8/31
System Analysis | Done | 9/1 | 9/12
Modelling | Done | 9/19 | 11/27
ER Diagram | Done | 9/19 | 9/26
Data Flow Diagram | Done | 9/26 | 10/3
Use case Diagram | Done | 10/10 | 10/17
Class Diagram | Done | 10/24 | 10/31
Activity Diagram | Done | 11/2 | 11/7
Sequence Diagram | Done | 11/7 | 11/14
Gantt & Budget Chart | Done | 11/14 | 11/27
Impliment | Done | 9/25 | 12/5
Creating django backend | Done | 9/6 | 10/4
Index page and home page | Done | 9/20 | 10/10
Log in and Signup | Done | 10/11 | 11/10
Create post | Done | 10/25 | 11/22
Created share | Done | 11/15 | 11/24
Created comment | Done | 11/24 | 11/30
Created like | Doing | 11/30 | 12/5
Testing | todo | 11/20 | 2024-08-12